## Priority 1 Tools
Objective | Target groups | Tool | Actions | Priority level | Planning | Owner | Budget | KPI | Status September
Increase membership | Prospect members | 1. IVIS | Sponsor and attend IVIS 2019 & approach potential members | 1 | Q3 2019 | Office & members | 7,000€ for sponsorship (not under COMMs budget) | Get 2 new full members to join | IVIS • Sponsorship agreement signed in May - 5,000€ • 100€ discount in registration fee for all VIPA members • Speaking slot to President • Collaterals for event advertisement in conference book (2 pages), conference bag insert, roll-up banner: all ready for printing/production in Japan Membership outreach • 1 academia member joined in March –Oak Ridge National Lab, USA • Key prospect members emailed with some support of members • Meetings at IVIS with prospect members
Increase membership & raise awareness | Prospect members; stakeholders; policy-makers; general public | 2. Website | 2.1 Website optimization internally & with developers); increasing website traffic & ranking; | 1 | 1) Q1 2019 | Office & developers | 1) Alias: 750 €; VIPA Office: 5h | Website traffic; new requests via website's contact form; new members | • SEO upgrade completed by Alias with support of office (re-drafting text of website) • LinkedIn page and Youtube banner logos added in upper-right corner • Changes to homepage: video box & better configuration of news section
|  |  | 2.2 Generate more content |  | 2) All 2019 |  |  |  | 4 press releases published, website sections have been re-drafted for SEO
|  |  | 2.3 Enhance Chinese section of the website/ evaluate other channels |  | 3) Q1 2019 |  |  |  | Agreed in board meeting Leeds not to invest on Chinese section of website cause not sure that's best platform to reach out to Chinese companies
|  | 3. Press releases | 3.1 Produce press releases (using sufficient keywords) or reuse press releases from the past in case new content is missing | 1 | 1) All 2019 | Members & office | 1) VIPA Office: 5h/press release |  | 4 press releases published, 1 technical bulletin
|  |  | 3.2 Translate press releases to Mandarin |  | 2) All 2019 |  | 2) Awaiting quote |  | Agreed in board meeting Leeds not to invest on Chinese translation because little value
|  | 4. Case studies | 4.1 Produce case studies (using sufficient keywords) or reuse case studies from the past | 1 | 1) All 2019 | Members & office | 1) VIPA Office: 3h/case study |  | • 1st case study published - Pouget Consultants 29 Jan • 2nd case study of Kingspan published in May
|  |  | 4.2 Make use of VIPA conference case studies |  | 2) Q1 2019 |  | 2) VIPA Office: 3h/case study |  | Case study Pouget Consultants 29 Jan
|  | 5. Newsletters | 5.1 Create newsletter bi-annually for members | 1 | 1) June & Dec 2019 | Office | 1&2) VIPA office: |  | Issued 2 September - on 9 Sept.: 41% open rate
|  |  | 5.2 Create external version of newsletter for website |  | 2) June & Dec 2019 |  | 5h per edition |  | To be issued September
|  | 6. Annual report | 6.1 Create annual report for 2019 | 1 | 1) Sept 2019 | Office | 1&2) VIPA Office: 10h |  | Annual Report was completed and sent to membership
|  |  | 6.2 Create external version of annual report |  | 2) Sept 2019 |  |  |  | Printed version to be used during IVIS for prospection. A reduced version of the Annual Report (without finances) will be added to the website
|  | 7. Promotional videos | Create further promotional videos (on different applications of VIPs) & promote, including via Build Up | 1 | All 2019 | Members & office | VIPA Office: average 20h / video |  | Video on appliances published on 23 July (1,800£): • Translations of subtitles added (DE, NL, SL, Chinese, JP, FR) • Added on Youku (equivalent of YouTube in China) • Start working on next video (packaging) after summer to time it with Dusseldorf event
|  | 8. LinkedIn account | 8.1 Create LinkedIn account (without external comments option) | 1 | 1) Q1 2019 | Members / office | 1&2) VIPA Office: 5h |  | • LinkedIn page created in March • 150€ banner for header, also used on Youtube channel • 61 followers on 9 September • 15 updates so far: 3/month
|  |  | 8.2 Define an indicative content planning, draft social media policy and identify spokesperson | [5 empty] | Social media policy and calendar with content completed and approved
|  | 9. Monitor regulatory developments | Monitor regulatory developments at EU level that can impact the VIP sector | 1 | All 2019 | Office | VIPA Office: 12h |  | On-going; Office to monitor European Parliament elections & EU institutions priorities for the next 5 years
|  | 10. Google Advert campaign | Create short Google Advert campaign to increase traffic on website | 1 | Q1/Q2 2019 | Office | VIPA Office: 10h |  | LinkedIn campaign was set up on 5 Sept.for 1 week : video campaign (video on use of VIPs in appliances) on very focused target group in Belgium, Germany, France - link to website page use of VIPs in appliances

## Priority 2&3 Tools
Objective | Target groups | Tool | Actions | Priority level | Planning | Owner | Budget | KPI | Status May
Increase membership & raise awareness | Prospect members, stakeholders & policy-makers | Manifesto | Create association position in view of new European Parliament & European Commission term | 2 | Q1 2019 | Members & office | VIPA Office: tbd Designer: tbd | Website traffic; new alliances | Decided in Board meeting Leeds not to do this in 2019
|  | Infographics | Create infographics with key figures on the sector (production volumes, employment, circularity, etc.), possibly from future market study | 2 | Q3 2019 | Office | VIPA Office: tbd Designer: tbd | Website traffic; requests contact form | Decided in Board meeting Leeds not to do this in 2019
|  | Webinars | Identify topics on which webinars could be created | 3 | Q3/Q4, if relevant | Members & office | VIPA Office: tbd Platform: tbd | Website traffic | Decided in Board meeting Leeds not to do this in 2019
|  | Interviews | Conduct interviews with stakeholders/policy-makers on key topics as they arise | 3 | Q3/Q4, if relevant | Members & office | VIPA Office: tbd Platform: tbd | Website traffic; new alliances | Decided in Board meeting Leeds not to do this in 2019
|  | Video statements | Create short video statements on key topics as they arise | 3 | Q3/Q4, if relevant | Members & office | VIPA Office: tbd Platform: tbd | Website traffic; new alliances | Decided in Board meeting Leeds not to do this in 2019
|  | Blog | Envisage creating a blog if sufficient content is being generated | 3 | Q3/Q4, if relevant | Office | VIPA Office: tbd | Website traffic | Decided in Board meeting Leeds not to do this in 2019